## Standard AOC
AOC Schedule of Events Template Civil Aviation Directorate - Initial Certification & Business Development Unit
Transport Malta, Malta Transport Centre, Pantar Road, Lija LJA 2021, Tel: +356 2555 5651; initialcert.tm@transport.gov.mt; www.transport.gov.mt.
PROPOSED DATES
|  | (Month 1) |  |  |  | (Month 2) |  |  |  | (Month 3) |  |  |  | (Month 4)
MILESTONES | STATUS | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3
A. Pre-Application Phase
A1 Pre-application meeting with CAD
A2 Submit SoE
A3 Revised POPS
A4 Incorporation of the company (MBR)
A5 Applicant request of ICAO 3 letter code & R/T callsign.
B. Formal Application Phase
B1 Submission of AOL application (form TM/CAD/0062) and related docs
B2 Submission of AOC and CAMO application (form TM/CAD/0068 and EASA form 2) with OM suite, CAME and checklists
B3 Submission of CAM subcontractor agreement and JPM (if applicable)
B4 Submission of NPs Nomination letter, CV and qualifications
B5 Submission of Part-ORO, -CAT and -SPA compliance checklists
B6 Submission of Part-CAMO compliance checklist
B7 Submission of audit plan
B8 Submission of Part-CAMO pre-audit report (organisation and subcontractor)
B9 Submission of CAMO MSAT
B10 Submission of CAMO manhour plan
B11 Submission of Service Level Agreement (Operations & dispatch)
B12 Submission of ERP
B13 Submission of MEL
B14 Submission of AMP
B15 Submit of FSTD approval (form TM/CAD/0225)
B16 Submission of RVSM / NAT-HLA approval (form TM/CAD/0099)
B17 Submission of LVO approval (form TM/CAD/0101)
B18 Submission of DG approval (form TM/CAD/0181)
B19 Submission of EFB application (form TM/CAD/0166)
B20 Submission of maintenance contracts
B21 Submission of CofA application (AITP-C01 Appendix I) and related documents
B22 Submission of CofR application (AITP-R-1 Appendix I) and related documents
B23 Submission of Security Manual (AVSEC)
B24 Submit request for Radio Station License (MCA)
B25 Formal application meeting and NPs interviews
B26 Formal acceptance of AOC application
C. Document Evaluation
C1 Receipt of CAD comments on OPS documents
C2 Receipt of CAD comments on Airworthiness documents
C3 Submission of amended OPS manuals
C4 Submission of amended AW documents
C5 Review of amended OPS manuals
C6 Review of amended AW documents
D. Other relevant milestones
D1 Flight Crew Induction / Conversion Training
D2 Training of contracted personnel (dispatch etc.)
D3 CAM subcontractor audit (pre-contract)
D4 OCC audit (pre-contract)
D5 Internal pre-AOC audit
D6 Internal pre-CAMO audit
D7 Subsciption to OEM data
D8 Office set-up
D9 Implementation of Compliance & Safety tools (software)
D10 Implementation of Maintenance Tracking Software
E. Demonstration phase
E1 CAM subcontractor audit
E2 OCC subcontractor audit
E3 Training inspection (simulator)
E4 CAMO secondary office audit
E5 OPS secondary office audit
E6 Demonstration flight
E7 CAMO audit (mani audit)
E8 Pre-AOC OPS audit (main office)
E9 Proving flight
F. Certification
F1 Security Manual approval
F2 OPS Manual Approvals
F3 MEL Approval
F4 CAME approval
F5 Issue of Part-CAMO approval
F6 AMP approval
F7 Issue of CofR
F8 Issue of CofA
F9 Issue of AOL, AOC & OPS Specs
Legend: | Completed | (Month 1) Week 2: In Progress; (Month 1) Week 4: Not yet commenced
INTRUCTIONS FOR THE APPLICANT
1. Insert company name into the header.
2. Enter proposed months and dates of completion into the planner
3. Submit to HIC and/or assigned inspector(s)
Form TM/CAD/0315/A Issue 4 – May 2024 Transport Malta is the Authority for Transport in Malta set up by Act XV of 2009

## AOC with One CAMO
AOC Schedule of Events Template Civil Aviation Directorate - Initial Certification & Business Development Unit
Transport Malta, Malta Transport Centre, Pantar Road, Lija LJA 2021, Tel: +356 2555 5651; initialcert.tm@transport.gov.mt; www.transport.gov.mt.
PROPOSED DATES
|  | (Month 1) |  |  |  | (Month 2) |  |  |  | (Month 3) |  |  |  | (Month 4)
MILESTONES | STATUS | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3
A. Pre-Application Phase
A1 Pre-application meeting with CAD
A2 Submit SoE
A3 Revised POPS
A4 Incorporation of the company (MBR)
A5 Applicant request of ICAO 3 letter code & R/T callsign.
A6 Pre-application meeting with the Authority responsible for the oversight of the CAMO
B. Formal Application Phase
B1 Submission of AOL application (form TM/CAD/0062) and related docs
B2 Submission of AOC application (form TM/CAD/0068) with OM suite and checklists
B3 Submission of CAM agreement (Appendix I to Part-M)
B4 Submission of NPs Nomination letter, CV and qualifications
B5 Submission of Part-ORO, -CAT and -SPA compliance checklists
B6 Submission of audit plan
B7 Submission of CAMO pre-contract audit
B8 Submission of risk register/hazard log
B9 Submission of Service Level Agreement (Operations & dispatch)
B10 Submission of ERP
B11 Submission of MEL
B12 Submit of FSTD approval (form TM/CAD/0225)
B13 Submission of RVSM / NAT-HLA approval (form TM/CAD/0099)
B14 Submission of LVO approval (form TM/CAD/0101)
B15 Submission of DG approval (form TM/CAD/0181)
B16 Submission of EFB application (form TM/CAD/0166)
B17 Submission of CofA application (AITP-C01 Appendix I) and related documents
B18 Submission of CofR application (AITP-R-1 Appendix I) and related documents
B19 Submission of Security Manual (AVSEC)
B20 Submit request for Radio Station License (MCA)
B21 Formal application meeting and NPs interviews
B22 Formal acceptance of AOC application
C. Document Evaluation
C1 Receipt of CAD comments on OPS documents
C2 Receipt of CAD comments on Airworthiness documents
C3 Submission of amended OPS manuals
C4 Submission of amended AW documents
C5 Review of amended OPS manuals
C6 Review of amended AW documents
D. Other relevant milestones
D1 Flight Crew Induction / Conversion Training
D2 Training of contracted personnel (dispatch etc.)
D3 CAMO audit (pre-contract)
D4 OCC audit (pre-contract)
D5 Internal pre-AOC audit
D6 Subsciption to OEM data
D7 Office set-up
D8 Implementation of Compliance & Safety tools (software)
E. Demonstration phase
E1 OCC subcontractor audit
E2 Training inspection (simulator)
E3 OPS secondary office audit
E4 Demonstration flight
E5 Pre-AOC OPS audit (main office)
E6 Proving flight
F. Certification
F1 Security Manual approval
F2 OPS Manual Approvals
F3 MEL Approval
F4 Amended Part-CAMO approval
F5 AMP approval
F6 Issue of CofR
F7 Issue of CofA
F8 Issue of AOL, AOC & OPS Specs
Legend: | Completed | (Month 1) Week 2: In Progress; (Month 1) Week 4: Not yet commenced
INTRUCTIONS FOR THE APPLICANT
1. Insert company name into the header.
2. Enter proposed months and dates of completion into the planner
3. Submit to HIC and/or assigned inspector(s)
Form TM/CAD/0315/B Issue 4 – May 2024 Transport Malta is the Authority for Transport in Malta set up by Act XV of 2009